Scenario-Based Validation POC

NVIDIA Cosmos on AWS  |  plan and execution checklist

Prepared: 18 June 2026     Domain: Autonomous driving / ADAS     Infrastructure: Self-hosted Cosmos on AWS GPUs

Objective

Stand up the NVIDIA Cosmos world foundation models on AWS and build a closed-loop scenario-based validation harness for an ADAS function. From a small set of seed clips we generate a large set of safety-relevant edge cases, run the system under test against them, and use an automated judge to score behaviour and surface failures. The output is a dashboard and an auditable validation report aligned to SOTIF (ISO 21448) and ISO 26262 thinking.

Solution at a glance

Figure 1. Four-phase pipeline: provision, generate, validate, present. The loop feeds new failures back into the scenario matrix.

Execution checklist

Owners and dates are placeholders for the kickoff meeting. Start Phase 1 quota requests on day one; they have the longest lead time.

Phase 0 - Scope and demo narrative      Day 1

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Confirm the single ODD slice to validate (e.g. urban intersection, pedestrian crossing) | Lead | One slice agreed in writing |
| ☐ | Select the system under test (open detector or simple planner) | ML | Model runs on a sample clip |
| ☐ | Write the one headline claim the demo must prove | Lead | One sentence approved |
| ☐ | Define success metrics (scenarios generated, failures found, coverage) | Lead | Metric targets set |

Phase 1 - Provision AWS and NVIDIA AI Enterprise      Days 1 to 3

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | File GPU quota increase for p5 / p4d and g6e | Cloud | Quota approved by AWS |
| ☐ | Subscribe to NVIDIA AI Enterprise in AWS Marketplace and capture the NGC key | Cloud | NGC login works |
| ☐ | Launch generation node from the NVIDIA AI Enterprise AMI | Cloud | nvidia-smi and GPU docker test pass |
| ☐ | Launch the small judge node (L40S or A100) | Cloud | Node reachable, GPU visible |
| ☐ | Create S3 bucket and attach EBS gp3 volume | Cloud | Read and write verified |
| ☐ | docker login nvcr.io and set the Hugging Face token | ML | Auth confirmed |

Phase 2 - Stand up Cosmos      Days 3 to 4

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Clone cosmos-predict2.5, cosmos-transfer2.5, cosmos-reason2, cosmos-cookbook | ML | Repos cloned |
| ☐ | Pull model checkpoints from Hugging Face | ML | Checkpoints downloaded |
| ☐ | Run one sample inference per model from the Cookbook | ML | Each model produces output |
| ☐ | Record per-model VRAM and runtime for sizing | ML | Sizing table filled |

Phase 3 - Generate scenarios      Days 4 to 7

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Ingest seed clips and run Cosmos Curator (filter, annotate, deduplicate) | ML | Clean seed set ready |
| ☐ | Author the scenario matrix config (weather, light, actors, behaviour, geometry) | ML | Matrix reviewed |
| ☐ | Generate variants with Cosmos Transfer using structured controls | ML | Variants render correctly |
| ☐ | Roll futures with Cosmos Predict for hazardous moments | ML | Future clips generated |
| ☐ | Write every clip and its metadata to the S3 manifest | ML | Manifest complete and reproducible |

Phase 4 - Validate      Days 7 to 10

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Run the system under test on every clip and capture outputs | ML | Outputs stored per clip |
| ☐ | Configure the Cosmos Reason rubric and return structured JSON verdicts | ML | Verdicts parse cleanly |
| ☐ | Score clip realism with Cosmos Evaluator | ML | Realism scores attached |
| ☐ | Calibrate the judge against Alpamayo-style references (optional) | ML | Calibration documented |
| ☐ | Aggregate results into a single scored results table | ML | Results table built |

Phase 5 - Present      Days 10 to 12

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Build the Streamlit dashboard (metrics, coverage heatmap, failure gallery) | ML | Dashboard runs locally |
| ☐ | Implement a mock mode so the dashboard runs without a GPU | ML | Runs on laptop |
| ☐ | Add the SOTIF / ISO 26262 one-page PDF export | ML | PDF exports correctly |
| ☐ | Pre-generate all demo assets | ML | Demo runs offline |

Phase 6 - Rehearse and present      Day 12

|  | Task | Owner | Acceptance criteria |
| --- | --- | --- | --- |
| ☐ | Dry-run the demo end to end | Lead | No live GPU dependency |
| ☐ | Lock the headline claim and the single dramatic failure clip | Lead | Story rehearsed |
| ☐ | Prepare the cost summary and the next-step ask | Lead | One-slide ask ready |

What a strong result looks like

✓  From a handful of seed clips, generate several hundred safety-relevant scenarios with no extra data collection.

✓  Surface failure modes the test fleet never encountered, each shown as a clip with the model output and a written verdict.

✓  Show coverage of the ODD as a heatmap, so gaps are visible at a glance.

✓  Export a one-page validation report that a safety lead can read and sign.

Key risks and mitigations

| Risk | Mitigation |
| --- | --- |
| GPU quota approval is slow | File on day one. Validate the judge node and Cosmos Reason while the large-instance quota is pending. |
| Generation throughput is limited | Keep clip counts modest. Generate in short batches, snapshot to S3, stop the large node between runs. |
| Judge reliability is questioned | Use a fixed rubric, add Cosmos Evaluator realism scores, and calibrate against Alpamayo-style references. |
| Scope creep | One ODD slice and one system under test for the POC. Depth over breadth. |
| Cost overrun | Run generation in bursts and shut the p5 / p4d node down. Keep only the small judge node warm. |